## Sheet1
I | Effects of infrastructure development works
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
1 | Inadequate amount of information on future infrastructure development works | Experience exchange between OEM Member States on the status of multi-annual rail infrastructure planning and financing schemes Better use of the investment plan of the RFC To draw the attention of the CNC on the missing links and non-coordinated investments of the corridor and organise a dialohue with the Coordinator on these issues (Reformulation proposed as example) |  | Presentation and discussion at Executive Board meeting | Core Network Corridor, Executive Board | 31st December 2016
|  | Continuously (every quarter of a year) updated webpage about the current scheduling of the implementation phase of the major infrastructure development projects (not the capacity restrictions) |  | CNC-hosted webpage active RFC Tasks. | Core Network Corridor Management Board | 30th November 2016
Reporting procedure approved by the Member States
|  | Alignment of the indicative investment plan in the CID |  | CID Book 5 extraordinary update | Management Board | 31st December 2016
3 | Lack of effective coordination of capacity restrictions | Application of the RNE guidelines concerning the coordination of works |  |  | Infrastructure Managers and Management Board
|  | Permanent exchange of information before submitting application for CEF Funding relating to works on the rail freight corridors |  | improvement of the coordination of works | Ministries and Infrastrcture Managers | Every year
|  | Establishing of a working group and a coordinator position responsible exclusively for the coordination of temporary capacity restrictions | Coordination of works - more commercial approach | Modification of the Internal Rules and Procedures | Management Board | 1st July 2016
|  | Finalisation of the capacity restrictions plan between X-17 and X-12 | Coordination of works - more commercial approach | Coordination meeting | Management Board | 11th December 2016
4 | Lately announced capacity restrictions | To apply the Corridor protocol on their publishing |  | Approved corridor protocol Feedback of the customers on quick information about extraordinary capacity restrictions | Management Board | 1st March 2016
|  | All extra costs (track access charges and running costs) of realignment of train path to be born by the respective infrastructure manager |  | CID 2018 (to be published in Jan 2017) | Management Board | 31st December 2016
2 | Capacity not protected between publishing and X-2 (except force majeure cases) | All extra costs (track access charges and running costs) of realignment of train path to be born by the respective infrastructure manager |  | CID 2018 (to be published in Jan 2017) | Management Board | 31st December 2016
|  | No pre-arranged train path is offered, only reserve capactiy |  | CID 2018 (to be published in Jan 2017) | Management Board | 31st December 2016
II | Traffic management
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
1 | No special care by the dispatchers yet Need for increasing the attention of the dispatchers on the international train running on corridor product | Identification of the trains using PaPs and reserve capacity in the internal traffic management rules |  | Modification of the legislative framework | Executive Board Infrastructure Managers? | TBD
To provide access to TIS as an addition tool for information in real time to the national dispatcher
|  | Appropriate ranking of the trains using PaPs and reserve capacity in the legislative priority list |  | Modification of the internal rules | Management Board Infrastructure Managers | TBD
2 | Statistics concern only the trains using PaPs and reserve capacity Monitoring of the performance of the international freight traffic running on the corridor | Application of electronic data exchange between TIS and the national systems (developement of interface => maybe improve the text) | To harmonize the relevant normatives to be similarly applied | TIS relieably displaying all trains of the respective infrastructure manager | Management Board C-OSS Manager | 11th December 2016
|  | Definitition of extended train sample | To harmonize the relevant normatives to be similarly applied | Update of the TPM Manual | Traffic Management WG C-OSS Manager | 30th November 2016
3 |  | To apply the RNE guidelines on KPIs |  |  | C-OSS Manager
etc.
III | Harmonisation of administratives and technical rules
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
1 | Mandatory technical checks for all trains | Trusted handover (please explain) and mutual recognition. Would it be useful to set up of joint training sessions with the responsibles stakholders ? => SPECIFY WHICH BORDER WHICH COUNTRIES | Principle of trust, project prioritzation, willingness is needed between the stakeholders | Reduction of the time at the borders | Railway undertakings => This action plan is not signed by RU so they cannot be designated here. | NR
2 | Different numbers of buffer wagons required between electric loco and dangerous goods wagons | Alignment to the provisions of RID | Certain traditional, unnecessary rules to be eliminated | Study on the risk assessment delivered | 3 infrastructure managers (study) | 31st December 2016
|  |  |  | Proposal for legislation | Management Board, Executive Board | 1st July 2017 | Giordano
3 | Different number of locomotive drivers | One locomotive driver operation for all locomotives equipped with vigilance control | Certain traditional, unnecessary rules to be eliminated | Proposal adaptation for legislation | Management Board, Executive Board NSA | 31st December 2017 | Giordano
4 | Locomotives of the same class but with different software versions need to be re-authorised | Deregulation of the approach | To simplify procedures and elimintate restrictive rules | Proposal for legislation | Management Board, Executive Board | 31st December 2017 | Ainoha
5 | Effects of temporary speed restrictions | Evaluation of all TSR-sections along the corridor together with approximate duration and impact analysis on time-table planning |  | Impact analysis | Management Board | 30th September 2016
etc.
IV | Charging
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
1 | Inadequate attrectiveness of PaPs and reserve capacity | TAC rebate under para. 3 Art. 33 of the recast |  | CID 2018 (to be published in Jan 2017) | Management Board | 31st December 2016 | Elisabeth
2 | Administrative burden of handling performance regime payments | Suspension of the performance regime for trains using PaPs or reserve capacity |  | CID 2018 (to be published in Jan 2017) | TBD | 31st December 2016 | Elisabeth
|  | Internal clearing mechanism for performance regime payments and common conditions for trains using PaPs and reserve capacity => Harmonisation of the timing of cancelation fee, ok. ?? | To streamline the cooperation with business partners | CID 2019 (to be published in Jan 2018) | TBD Infrastructure managers | 31st December 2017
3 | Fragmened information sources on TAC | Brochure on charging including sample calculations |  | Brochure delivered | Secretariat | 1st October 2016
|  | Charging Information System integrated into PCS | To streamline the cooperation with business partners | CIS active | TBD Infrastructure managers | TBD
4 | Complicated track charging system | Common track charging system for trains using PaPs and reserve capacity | To streamline the cooperation with business partners | CID 2020 (to be published in Jan 2019) | Management Board | 31st December 2018 | Elisabeth
etc.
V | Other GOVERNANCE and Tools
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
1 | Lack of interest in using common IT systems | Creation of interfaces with the national systems |  |  | TBD
|  | Common database for all IT systems |  |  | TBD
|  | Simplification of after sales procedures, such as the cancellation of running days (train paths) |  |  | TBD
2 | Possible inadequate involvement of the railway undertakings in the decision-making procedure | Limited participation of the RUs at the meetings of the Executive Board Permanent time slot on the agenda of the ExBo for the spokeperson of the RAG and TAG , where relevant |  | amendment of the IRP | Executive Board | 31st December 2016 Why not next ExBo following this MoU
|  | Limited participation of the RUs at the meetings of the Management Board | To streamline the cooperation with business partners | amendment of the IRP | Management Board | 30th June 2016
3 | Possible incoherency of the strategic planning on different levels | Organising 1 meeting once year dedicated to the strategic issues, overview of the investment planning on the corridor | To streamline the cooperation with business partners | Joint EB and MB meeting | Executive Board Management Board | 30th November 2016
4 | Duplication of border clearance procedures (border police, customs) at both sides of border crossings | Bilateral agreements on common border clearance procedures |  | Bilateral agreements concluded SPECIFY | Member States SPECIFY | about 2 years from now?
VI | On-going activities => to be delete because either already covered by the Regulation, either already undertaken
| Stumbling blocks | Potential Solutions | Coherence to the recommendations made by OEM CNC Coordinator | Indicator | Respective Actors Responsibles | Realistic Deadline
|  | Designation of PaPs matches the market need with the offered capacities by IMs | To streamline close consultation and cooperation with RUs | Match the market need with the offered capacities by IMs | C-OSS Manager | 11th January 2016
|  | Organising regular meetings with RUs and Terminals |  | Once a year to hold a meeting about the startegic goals on the corridor - TAG/RAG meeting | Management Board | 30th November 2016
|  | Publication of annual performance and results done on the corridor |  | Annual Report | Management Board | 31th July 2016
|  | Origanising Customer Satisfaction Survey, analyse the outcome |  | RNE Survey | Management Board | 15th October 2016
|  | Participation in the RNE-projects dedicated to the corridor operation |  | TBD | Management Board
|  | Representation the corridor interest at RFC-Talk meetings |  | Common approved RFC-Talk conclusions | Management Board
| Missing issues listed in the Cross border WG are : | Still existing lack of track capacity in Curtici and on Bekescsaba – Lökösháza line: 2nd track foreseen after 2017
Still time-consuming: obligation to wait for other locomotive
Certain traditional operational rules are existing with no specific purpose, that should be jointly identified and eliminated (non-sense rules)
Still, normative differences between Corridor countries, although common regulations (UIC; TSI; COTIF) exist but not similarly applied  harmonization needed => Are there any other than the buffering wagons?
Optimize the locomotive availability
Note on B15: BUY Julie (MOVE): Please clarfiy, do you mean a proytection of the Pap till the running day. What do you mean by protection ? I don't see the link between the potential solutions and the stumbling block
Note on B31: BUY Julie (MOVE): To specify which country
Note on B37: BUY Julie (MOVE): We have to discuss this
Note on B42: BUY Julie (MOVE): We have to discuss this
Note on B51: DG MOVE - B2: To be consistent with the draft Rotterdam declaration.
Note on C5: BUY Julie (MOVE): Why the info on the financing scheme is needed? This should be covered by the permanent update of the investment plan of the RFC?
Note on C8: BUY Julie (MOVE): This-is an obligation of the Regulation
Note on C11: DG MOVE - B2: Good ! Is it in line with RNE Guidelines?
Note on C16: BUY Julie (MOVE): Here, you clarify that PaP is not RC?
Note on C21: DG MOVE - B2: Is it in law or in NS?
Note on C23: BUY Julie (MOVE): Performance should monitor the full traffic at the borders. What do you mean by extended train sample?
Note on C33: DG MOVE - B2: We understand that it would be for all the international trafic running on the corridor (meaning crossing at least one border)
Note on C38: BUY Julie (MOVE): We have to discuss this
Note on C46: BUY Julie (MOVE): to specify countries What is exactly missing
Note on C50: DG MOVE - B2: MaBo has to participate in the RAG TAG so no need to duplicate the meeting.
Note on C52: BUY Julie (MOVE): To Move in chapter IV harmonisation of administrative and technical rules and Specify which and where.
Note on D22: BUY Julie (MOVE): I don't see the coherence with the recommandation of the CNC
Note on E7: BUY Julie (MOVE): Please explain
Note on E19: BUY Julie (MOVE): Is it the law or the NS?
Note on E21: BUY Julie (MOVE): Is it the law or the NS?
Note on E23: BUY Julie (MOVE): TIS take into account any train crossing a border on th ecorridor, this is the corridor train.
Note on E29: DG MOVE - B2: This more a pre-solution?
Note on E30: BUY Julie (MOVE): to be more specific
Note on E31: DG MOVE - B2: is it foreseen by law ? Or the law is flexible and it is an approach of the NSA to require 2 drivers?
Note on F29: BUY Julie (MOVE): to specify who